## Sheet1
Work Breakdown Structure
ID | Task | Dependencies | Status | Effort (Hours) | Cost | Start Date | Planned Completion | Estimate to Completion | Actual Completion | Resources
1 | Research Phase | None | In Progress | 20 | 0 | 2024-11-05 | 2024-11-11 | 2024-11-11 | N/A | Self
2 | Data Collection | Task 1 | Not Started | 30 | 0 | 2024-11-12 | 2024-11-18 | 2024-11-18 | N/A | Self
3 | Model Development | Task 1, 2 | Not Started | 50 | 0 | 2024-11-19 | 2024-12-02 | 2024-12-02 | N/A | Self
4 | System Structure Design | Task 1 | Not Started | 40 | 0 | 2024-12-03 | 2024-12-09 | 2024-12-09 | N/A | Self
5 | Data Preprocessing and Feature Extraction | Task 2,3 | Not Started | 35 | 0 | 2024-12-10 | 2024-12-16 | 2024-12-16 | N/A | Self
6 | Model Training | Task 3,5 | Not Started | 40 | 0 | 2024-12-17 | 2024-12-23 | 2024-12-23 | N/A | Self
7 | Testing and Validation | Task 6 | Not Started | 30 | 0 | 2024-12-24 | 2024-12-30 | 2024-12-30 | N/A | Self
8 | System Integration | Task 3, 4 | Not Started | 40 | 0 | 2024-12-31 | 2025-01-06 | 2025-01-06 | N/A | Self
9 | UI/UX Design | Task 4 | Not Started | 30 | 0 | 2025-01-07 | 2025-01-13 | 2025-01-13 | N/A | Self
10 | Performance Optimization | Task 7,8 | Not Started | 20 | 0 | 2025-01-14 | 2025-01-20 | 2025-01-20 | N/A | Self
11 | Final Testing | Task 10 | Not Started | 30 | 0 | 2025-01-21 | 2025-01-27 | 2025-01-27 | N/A | Self
12 | Documentation and Reporting | Task 9, 11 | Not Started | 20 | 0 | 2025-01-21 | 2025-01-27 | 2025-01-27 | N/A | Self
13 | Deployment and Presentation | Task 11 | Not Started | 20 | 0 | 2025-01-21 | 2025-01-27 | 2025-01-27 | N/A | Self

## Sheet2
Project Completion Criteria Table
ID | Completion Criteria | Description
1 | AI Model Development | Both known and novel dangers may be detected by the fully built AI model
2 | Threat Detection Accuracy | A high detection accuracy rate with few false positives and negatives must be attained by the system
3 | Real-Time Response Capability | Without slowing down network traffic, the system recognizes and reacts to threats instantly.
4 | Automated Threat Mitigation | Through the isolation or blockage of harmful activities, the system automatically reduces dangers.
5 | User Interface Functionality | Both technical and non-technical users may easily navigate the dashboard thanks to the user interface
6 | Scalability of the System | To manage growing network traffic and more datasets, the system has to be scalable.
7 | Performance and System Optimization | The system has to run smoothly with low latenccy, optimal memory and CPU use and more
8 | Security and Data Protection | Access control is in place for system users, and all data handled by the system is encypted.
9 | Documentation and Reporting | Thorough documentatiom is finished, including sytem architecture, user manuals, and test results
10 | Final Testing and Validation | All test cases, including those for security validation, usability, and performance, are passed by the system.
11 | Deployment and Presentation | After successfully deploying in a test environment, the system is shown off.

## Sheet3
Assumptions and Constraints Table
ID | Description | Type | Comments | Status | Date Entered
1 | Access to high- quality, labeled training datasets | Assumption | It is expected that the AI model can be trained using suitable, labeled datasets for both harmful and legitimate traffic | Active | N/A
2 | Real-time processing capability of the system | Assumption | The hardware of the system is supposed to be able to process network data in real time without experiencing any performance issues. | Active | N/A
3 | Machine learning models will generalize to new threats | Assumption | Based on their learning from known patterns, the trained AI models are expected to be able to generalize and identify new, undiscovered risks | Active | N/A
4 | Network infrastructure will not significantly change | Assumption | Throughout the project's lifespan, it is anticcipated that the underslying network infrastructure would not change much. | Active | N/A
5 | System will be scalable to handle increased traffic | Constraint | The system must be scalable to accommodate growing network traffic levels without experiencing performance deterioration. | Active | N/A
6 | Limited access to real-world cyberattack data | Constraint | Access to real-world attack data may be restricted due to privacy and security considerations, which might limit the model's capacity to be tested on live data. | Active | N/A
7 | Response time must be minimal | Constraint | The system must be able to identify and react to threats quickly, with little disruption to regular network operations. | Active | N/A
8 | Legal and compliance requirements for data security | Constraint | When handling sensitive data, the project must abide by lefal and regulatory regulations, such as GDPR, pertaining to data protection and security. | Active | N/A
9 | Budget limitations for hardware and software | Constraint | The project's capacity to purchase cutting-edge hardware or commerical software may be hampered by financial constrants. | Active | N/A